## Dashboard
AI Operating System
As of Fri 2 Oct 2026 · Sample PM |  |  |  | SAMPLE DATA. Open AI-OS.xlsx for the blank workbook.
| OPEN DECISIONS |  |  | UNCONFIRMED | OPEN CONFLICTS |  |  | JIRA NEEDING ATTENTION | DONE THIS WEEK
| 4 |  |  | 3 | 1 |  |  | 6 | 6
| 2 past 7 days |  |  | 1 older than 5 days | inventory stands until settled |  |  | of 15 in flight · 2 critical | 3 last week · 2 answers reused
Needs you |  |  | Open decisions, conflicts and unconfirmed items, worst first. Paste the last column into Cowork.
# | ID | Type | Topic | Summary | Age (d) | Severity | From | Say this
1 | INV-0007 | Decision | complaint-triage | Decide whether complaint triage routes to humans only or auto-closes low-severity. | 11 | Critical | L. Brooks | decide INV-0007: <outcome>
2 | INV-0009 | Decision | fraud-alerts | Fund a second data engineer for fraud alert prioritization, or slip Design by a month. | 9 | Critical | K. Ito | decide INV-0009: <outcome>
3 | INV-0013 | Conflict | fraud-alerts | Jira shows fraud alert model in Design; vendor says build started. Inventory stands until confirmed. | 5 | Critical | Vendor PM | decide INV-0013: <which version stands>
4 | INV-0012 | Know | mrm | MRM may add a bias test requirement for any credit-adjacent model. | 6 | Warning | R. Chen | confirm INV-0012
5 | INV-0014 | Decision | vendor-copilot | Accept the vendor pilot or run a competitive eval first. | 4 | Warning | S. Ruiz | decide INV-0014: <outcome>
6 | INV-0015 | New | chat-deflection | Chat deflection hit 31% containment in week 2, above the 25% target. | 3 | On track | Digital team | confirm INV-0015
7 | INV-0016 | Decision | council | Pick the Q1 intake cutoff date so the Council can size capacity. | 2 | On track | M. Okafor | decide INV-0016: <outcome>
8 | INV-0018 | New | complaint-triage | Complaints team can provide 3 months of labelled data by Oct 15. | 0 | On track | L. Brooks | confirm INV-0018
9
10
Jira needing attention |  |  | Flagged, past due, unmapped, or idle past the stage limit on the Config sheet.
# | Key | Stage | Assignee | Summary | Idle (d) | Health |  | Why | Say this
1 | AIUC-103 | Design | K. Ito | Fraud alert prioritization | 18 | Critical |  | Flagged as an impediment | draft Jira update for AIUC-103
2 | AIUC-116 | Approval | P. Shah | HR policy chatbot | 8 | Critical |  | Past due since 2026-10-01 | draft Jira update for AIUC-116
3 | AIUC-107 | Approval | P. Shah | Marketing copy assistant | 16 | Warning |  | No update in 16 days (limit 14) | draft Jira update for AIUC-107
4 | AIUC-115 | Discovery | Sample PM | RM email auto-drafting | 13 | Warning |  | No update in 13 days (limit 10) | draft Jira update for AIUC-115
5 | AIUC-105 | Triage | Sample PM | Collections outreach timing | 12 | Warning |  | No update in 12 days (limit 7) | draft Jira update for AIUC-105
6 | AIUC-109 | Unmapped | K. Ito | Wire fraud anomaly detection | 6 | Warning |  | Status 'Waiting for Vendor' is not in the Config map | draft Jira update for AIUC-109
7
8
9
10
Pipeline by stage |  |  | Open Jira issues per stage.
| Stage | Open | Attention | Stale after
| Intake | 1 | 0 | 7 days
| Triage | 2 | 1 | 7 days
| Discovery | 2 | 1 | 10 days
| Design | 2 | 1 | 14 days
| Approval | 2 | 2 | 14 days
| Delivery | 1 | 0 | 14 days
| Scale | 2 | 0 | 14 days
| Value | 2 | 0 | 45 days
| Unmapped | 1 | 1 | add to Config map
Done this week |  |  | Feeds the weekly report. Say: done: <what you finished>
| Date | Topic | Accomplishment
| 2026-10-02 |  | Completed intake review for statement insight summaries.
| 2026-10-01 | kyc-extract | Logged KYC accuracy regression and opened vendor ticket.
| 2026-09-30 | chat-deflection | Chat deflection week-2 readout sent to Digital leadership.
| 2026-09-29 | fraud-alerts | Escalated fraud alert staffing gap to Council agenda.
| 2026-09-28 | council | Built the value tracker template the Council asked for.
| 2026-09-28 |  | Unblocked loan pre-fill architecture review with Enterprise Architecture.
Accomplishments per week |  |  | Last eight weeks.
| Week of | Done
| 2026-08-10 | 0
| 2026-08-17 | 0
| 2026-08-24 | 3
| 2026-08-31 | 2
| 2026-09-07 | 4
| 2026-09-14 | 3
| 2026-09-21 | 3
| 2026-09-28 | 6

## Inventory
ID | Date | Type | Topic | Summary | From | Channel | Confidence | Ref | Jira | State | Age (days) | Severity | Rank key | Say this
INV-0001 | 2026-09-08 | New | council | AI Council moves to biweekly through Q4; next sitting Oct 8. | M. Okafor | Meeting | Confirmed |  |  | Logged | 24
INV-0002 | 2026-09-11 | Know | mrm | Model Risk now wants a validation plan at Design exit, not Approval. | R. Chen | Email | Confirmed |  |  | Logged | 21
INV-0003 | 2026-09-13 | Decision | call-summary | Go / no-go on expanding call summarization from 40 to 400 agents. | D. Patel | Meeting | Confirmed |  | AIUC-101 | Closed | 19
INV-0004 | 2026-09-15 | New | vendor-copilot | Vendor offering a 90-day no-cost pilot of agent assist for collections. | S. Ruiz | Email | Confirmed |  |  | Logged | 17
INV-0005 | 2026-09-18 | Know | genai-policy | GenAI usage policy v3 heard to ban customer data in prompts outright. | T. Nguyen | Teams | Unconfirmed |  |  | Confirmed | 14
INV-0006 | 2026-09-20 | Resolved | call-summary | Approved: expand to 400 agents, with weekly QA sampling for 6 weeks. | AI Council | Meeting | Confirmed | INV-0003 | AIUC-101 | Logged | 12
INV-0007 | 2026-09-21 | Decision | complaint-triage | Decide whether complaint triage routes to humans only or auto-closes low-severity. | L. Brooks | Meeting | Confirmed |  | AIUC-102 | Open | 11 | Critical | 3011.0001 | decide INV-0007: <outcome>
INV-0008 | 2026-09-22 | Confirmed | genai-policy | Policy v3 confirmed by Compliance: no customer data in prompts. | T. Nguyen | Email | Confirmed | INV-0005 |  | Logged | 10
INV-0009 | 2026-09-23 | Decision | fraud-alerts | Fund a second data engineer for fraud alert prioritization, or slip Design by a month. | K. Ito | Meeting | Confirmed |  | AIUC-103 | Open | 9 | Critical | 3009.0001 | decide INV-0009: <outcome>
INV-0010 | 2026-09-24 | Know | kyc-extract | KYC extraction vendor SOC 2 report expires Nov 30. | Procurement | Email | Confirmed |  | AIUC-104 | Logged | 8
INV-0011 | 2026-09-25 | New | council | Council wants a one-page value tracker for every use case in Scale. | M. Okafor | Meeting | Confirmed |  |  | Logged | 7
INV-0012 | 2026-09-26 | Know | mrm | MRM may add a bias test requirement for any credit-adjacent model. | R. Chen | Call | Unconfirmed |  |  | Unconfirmed | 6 | Warning | 2006.0001 | confirm INV-0012
INV-0013 | 2026-09-27 | Conflict | fraud-alerts | Jira shows fraud alert model in Design; vendor says build started. Inventory stands until confirmed. | Vendor PM | Email | Unconfirmed | INV-0009 | AIUC-103 | Open | 5 | Critical | 3005.0001 | decide INV-0013: <which version stands>
INV-0014 | 2026-09-28 | Decision | vendor-copilot | Accept the vendor pilot or run a competitive eval first. | S. Ruiz | Email | Confirmed |  |  | Open | 4 | Warning | 2004.0002 | decide INV-0014: <outcome>
INV-0015 | 2026-09-29 | New | chat-deflection | Chat deflection hit 31% containment in week 2, above the 25% target. | Digital team | Teams | Unconfirmed |  | AIUC-108 | Unconfirmed | 3 | On track | 1003.0002 | confirm INV-0015
INV-0016 | 2026-09-30 | Decision | council | Pick the Q1 intake cutoff date so the Council can size capacity. | M. Okafor | Meeting | Confirmed |  |  | Open | 2 | On track | 1002.0002 | decide INV-0016: <outcome>
INV-0017 | 2026-10-01 | Know | kyc-extract | KYC extraction accuracy on passports dropped to 91% after the vendor model update. | QA | Document | Confirmed |  | AIUC-104 | Logged | 1
INV-0018 | 2026-10-02 | New | complaint-triage | Complaints team can provide 3 months of labelled data by Oct 15. | L. Brooks | Teams | Unconfirmed |  | AIUC-102 | Unconfirmed | 0 | On track | 1000.0002 | confirm INV-0018
Note on A1: INV-0001, INV-0002 ... next number after the last row.
Note on B1: Date the information arrived. YYYY-MM-DD.
Note on C1: New = What's New. Know = What We Need to Know. Decision = Decision Needed. Conflict = disagrees with the inventory. Confirmed / Resolved close an earlier row named in Ref.
Note on D1: Topic slug from the Topics sheet.
Note on E1: One sentence. No customer data.
Note on F1: Person it came from.
Note on G1: Meeting, Email, Teams, Call, Document, Jira, Session.
Note on H1: Confirmed if first-hand or verified; Unconfirmed if second-hand.
Note on I1: For Confirmed, Resolved or Conflict: the INV ID it refers to.
Note on J1: Related Jira key, if any.
Note on K1: Computed. Cowork never writes here.
Note on L1: Computed. Cowork never writes here.
Note on M1: Computed. Cowork never writes here.
Note on N1: Computed. Cowork never writes here.
Note on O1: Computed. Cowork never writes here.

## Jira
Key | Summary | Status | Type | Priority | Assignee | Created | Updated | Due | Flagged | Labels | Topic | Stage | Days idle | Stale after | Health | Why | Rank key | Say this | Link
AIUC-101 | Contact center call summarization | Scaling | Epic | High | D. Patel | 2026-04-25 | 2026-09-29 | 2026-11-01 |  | genai | call-summary | Scale | 3 | 14 | On track |  |  |  | open
AIUC-102 | Complaint triage and routing | Discovery | Epic | High | L. Brooks | 2026-07-24 | 2026-10-01 | 2026-10-22 |  | nlp | complaint-triage | Discovery | 1 | 10 | On track |  |  |  | open
AIUC-103 | Fraud alert prioritization | Design | Epic | Highest | K. Ito | 2026-06-29 | 2026-09-14 | 2026-09-28 | Y | fraud | fraud-alerts | Design | 18 | 14 | Critical | Flagged as an impediment | 3018 | draft Jira update for AIUC-103 | open
AIUC-104 | KYC document extraction | In Delivery | Epic | High | A. Silva | 2026-05-25 | 2026-09-23 | 2026-10-27 |  | vendor | kyc-extract | Delivery | 9 | 14 | On track |  |  |  | open
AIUC-105 | Collections outreach timing | Triage | Epic | Medium | Sample PM | 2026-09-12 | 2026-09-20 |  |  | ml | vendor-copilot | Triage | 12 | 7 | Warning | No update in 12 days (limit 7) | 2012.0001 | draft Jira update for AIUC-105 | open
AIUC-106 | Branch staffing forecast | Value Tracking | Epic | Medium | J. Moore | 2025-12-06 | 2026-09-12 |  |  | forecast |  | Value | 20 | 45 | On track |  |  |  | open
AIUC-107 | Marketing copy assistant | Approval | Epic | Medium | P. Shah | 2026-08-03 | 2026-09-16 | 2026-10-12 |  | genai |  | Approval | 16 | 14 | Warning | No update in 16 days (limit 14) | 2016.0001 | draft Jira update for AIUC-107 | open
AIUC-108 | Chat deflection FAQ assistant | Scaling | Epic | High | Digital team | 2026-03-16 | 2026-09-30 |  |  | genai | chat-deflection | Scale | 2 | 14 | On track |  |  |  | open
AIUC-109 | Wire fraud anomaly detection | Waiting for Vendor | Epic | High | K. Ito | 2026-08-18 | 2026-09-26 |  |  | fraud | fraud-alerts | Unmapped | 6 |  | Warning | Status 'Waiting for Vendor' is not in the Config map | 2006.0001 | draft Jira update for AIUC-109 | open
AIUC-110 | Statement insight summaries | Intake | Story | Low | Sample PM | 2026-09-27 | 2026-09-27 |  |  | genai |  | Intake | 5 | 7 | On track |  |  |  | open
AIUC-111 | Loan document pre-fill | Design | Epic | Medium | A. Silva | 2026-08-13 | 2026-09-28 | 2026-11-11 |  | ocr |  | Design | 4 | 14 | On track |  |  |  | open
AIUC-112 | Teller balancing assistant | Declined | Epic | Low | J. Moore | 2026-07-04 | 2026-09-02 |  |  |  |  | Closed | 30 |  | Closed |  |  |  | open
AIUC-113 | ATM cash forecasting | Value Tracking | Epic | Medium | J. Moore | 2025-08-28 | 2026-09-22 |  |  | forecast |  | Value | 10 | 45 | On track |  |  |  | open
AIUC-114 | Dispute intake summarizer | Triage | Epic | High | L. Brooks | 2026-09-17 | 2026-09-30 |  |  | genai | complaint-triage | Triage | 2 | 7 | On track |  |  |  | open
AIUC-115 | RM email auto-drafting | Discovery | Epic | Medium | Sample PM | 2026-08-28 | 2026-09-19 |  |  | genai |  | Discovery | 13 | 10 | Warning | No update in 13 days (limit 10) | 2013.0002 | draft Jira update for AIUC-115 | open
AIUC-116 | HR policy chatbot | In Review | Epic | Low | P. Shah | 2026-08-23 | 2026-09-24 | 2026-10-01 |  | genai | genai-policy | Approval | 8 | 14 | Critical | Past due since 2026-10-01 | 3008.0002 | draft Jira update for AIUC-116 | open
Note on A1: Issue key, e.g. AIUC-104.
Note on C1: Exactly as Jira shows it. Mapped to a stage on the Config sheet.
Note on G1: YYYY-MM-DD
Note on H1: YYYY-MM-DD. Drives staleness.
Note on I1: YYYY-MM-DD or blank.
Note on J1: Y if flagged / impediment / labelled blocked.
Note on L1: Topic slug, if it maps to one.
Note on M1: Computed. Cowork never writes here.
Note on N1: Computed. Cowork never writes here.
Note on O1: Computed. Cowork never writes here.
Note on P1: Computed. Cowork never writes here.
Note on Q1: Computed. Cowork never writes here.
Note on R1: Computed. Cowork never writes here.
Note on S1: Computed. Cowork never writes here.
Note on T1: Computed. Cowork never writes here.

## Done
Date | Accomplishment | Topic | Jira | Source | Week of | This week | Rank key
2026-08-25 | Ran first front-door triage; 6 ideas in, 2 declined with reasons logged. | council |  | Session | 2026-08-24
2026-08-27 | Published the eight-stage operating model to the team SharePoint. | council |  | Session | 2026-08-24
2026-08-30 | Closed MRM questions on call summarization validation plan. | call-summary | AIUC-101 | Email | 2026-08-24
2026-09-01 | Set baseline for complaint triage: 4.2 day median time to route. | complaint-triage | AIUC-102 | Session | 2026-08-31
2026-09-05 | Got Procurement to start vendor risk review for KYC extraction. | kyc-extract | AIUC-104 | Email | 2026-08-31
2026-09-07 | Council approved chat deflection scale-up to all web traffic. | chat-deflection | AIUC-108 | Calendar | 2026-09-07
2026-09-08 | Retired the old intake spreadsheet; Jira is now the only intake path. | council |  | Session | 2026-09-07
2026-09-12 | Agreed staleness thresholds per stage with delivery leads. | council |  | Teams | 2026-09-07
2026-09-13 | Drafted the go/no-go memo for call summarization expansion. | call-summary | AIUC-101 | Session | 2026-09-07
2026-09-15 | Mapped GenAI policy v3 controls to every in-flight GenAI use case. | genai-policy |  | Session | 2026-09-14
2026-09-19 | Call summarization expansion approved by Council (INV-0006). | call-summary | AIUC-101 | Calendar | 2026-09-14
2026-09-20 | Declined teller balancing assistant; value case under $50K. | council | AIUC-112 | Session | 2026-09-14
2026-09-21 | Wrote the data request for complaint triage labelled history. | complaint-triage | AIUC-102 | Email | 2026-09-21
2026-09-22 | Ran Review Gate on the Q4 roadmap deck; fixed 3 MECE gaps. | council |  | Session | 2026-09-21
2026-09-26 | Confirmed GenAI policy v3 wording with Compliance (INV-0008). | genai-policy |  | Email | 2026-09-21
2026-09-28 | Unblocked loan pre-fill architecture review with Enterprise Architecture. |  | AIUC-111 | Teams | 2026-09-28 | Yes | 2026-09-28
2026-09-28 | Built the value tracker template the Council asked for. | council |  | Session | 2026-09-28 | Yes | 2026-09-28
2026-09-29 | Escalated fraud alert staffing gap to Council agenda. | fraud-alerts | AIUC-103 | Session | 2026-09-28 | Yes | 2026-09-29
2026-09-30 | Chat deflection week-2 readout sent to Digital leadership. | chat-deflection | AIUC-108 | Email | 2026-09-28 | Yes | 2026-09-30
2026-10-01 | Logged KYC accuracy regression and opened vendor ticket. | kyc-extract | AIUC-104 | Session | 2026-09-28 | Yes | 2026-10-01
2026-10-02 | Completed intake review for statement insight summaries. |  | AIUC-110 | Session | 2026-09-28 | Yes | 2026-10-02
Formulas:
Week of = IF([Date]="","",[Date]-WEEKDAY([Date],3))
Rank key = IF([This week]="Yes",[Date]+ROW()/100000,"")
Note on A1: Day it was done.
Note on B1: Outcome, not activity. 'Got MRM sign-off on X', not 'met with MRM'.
Note on C1: Topic slug.
Note on D1: Related key, if any.
Note on E1: Session, Email, Teams, Calendar: where it was found.
Note on F1: Computed. Cowork never writes here.
Note on G1: Computed. Cowork never writes here.
Note on H1: Computed. Cowork never writes here.

## Answers
ID | Date | Question | Kind | Answer or route | Source | Asked by | Ref | Times reused
Q-0001 | 2026-09-02 | Who approves a new GenAI use case? | Answer | The AI Council at the Approval gate; the PM owner brings it. | Operating model, gate table | B. Ford |  | 1
Q-0002 | 2026-09-06 | Can we use customer emails to fine-tune a model? | Routed | Routed to Compliance (T. Nguyen). Not answered here. | T. Nguyen | S. Ruiz |  | 0
Q-0003 | 2026-09-11 | What does Model Risk need at Design exit? | Answer | Validation plan, monitoring design, audit trail spec. | INV-0002; MRM standard 4.3 | P. Shah |  | 1
Q-0004 | 2026-09-17 | Who approves a new GenAI use case? | Reuse | Same as Q-0001. | Q-0001 | A. Silva | Q-0001 | 0
Q-0005 | 2026-09-20 | How long should Triage take? | Answer | Seven days before it is flagged stale. | Config sheet, stage table | L. Brooks |  | 0
Q-0006 | 2026-09-24 | Where do I submit a new AI idea? | Answer | Jira intake form in project AIUC. | AIUC intake form | New hire |  | 0
Q-0007 | 2026-09-27 | What does Model Risk need at Design exit? | Reuse | Same as Q-0003. | Q-0003 | K. Ito | Q-0003 | 0
Q-0008 | 2026-10-01 | Can a vendor model go to Scale before SOC 2 renewal? | Routed | Routed to Procurement / Third-Party Risk. | Third-Party Risk team | A. Silva |  | 0
Note on A1: Q-0001, Q-0002 ...
Note on C1: As asked, minus anything personal.
Note on D1: Answer = traced to a source. Routed = sent to a person or resource. Reuse = an earlier answer given again (put its ID in Ref).
Note on F1: Link or document the answer traces to, or the person routed to.
Note on H1: For Reuse: the Q ID reused.
Note on I1: Computed. Cowork never writes here.

## Reviews
Date | Artifact | Author | Passed | Failed | Verdict | Top fix
2026-09-10 | Q4 AI roadmap deck v2 | Sample PM | 5 | 3 | Fix first | Sections 2 and 4 overlap on capacity; merge them so the asks are MECE.
2026-09-22 | Q4 AI roadmap deck v3 | Sample PM | 8 | 0 | Ready
2026-09-26 | Fraud alert staffing ask | K. Ito | 6 | 2 | Fix first | The ask has no date or owner; say who decides by when.
2026-09-30 | Chat deflection week-2 readout | Digital team | 7 | 1 | Ready | Containment number needs its source and date.
Note on B1: File name or link.
Note on D1: Checks passed (of 8).
Note on E1: Checks failed.
Note on F1: Ready, or Fix first.
Note on G1: The single most important fix.

## Changes
Date | What changed | From | To | References updated | Approved by
2026-09-08 | Retired old intake tracker | OneDrive/AI/Intake.xlsx | Archive/Intake-2026Q3.xlsx | Topics: council notes doc; Answers Q-0006 | Sample PM
2026-09-23 | Moved fraud notes into topic doc | Documents/fraud-notes.docx | AI-OS/Topics/fraud-alerts.docx | Topics sheet row fraud-alerts | Sample PM
Note on E1: Where links were fixed.

## Topics
Topic | Name | Owner | Forum | Jira label | Status | Notes doc | Open items | Jira issues | Jira attention
council | AI Council and portfolio governance | M. Okafor | Council |  | Active | AI-OS/Topics/council.docx | 1 | 0 | 0
call-summary | Contact center call summarization | D. Patel | Council | AIUC-101 | Active | AI-OS/Topics/call-summary.docx | 0 | 1 | 0
complaint-triage | Complaint triage and routing | L. Brooks | Standup | AIUC-102 | Active | AI-OS/Topics/complaint-triage.docx | 2 | 2 | 0
fraud-alerts | Fraud alert prioritization | K. Ito | Council | fraud | Active | AI-OS/Topics/fraud-alerts.docx | 2 | 2 | 2
kyc-extract | KYC document extraction | A. Silva | Standup | AIUC-104 | Active | AI-OS/Topics/kyc-extract.docx | 0 | 1 | 0
mrm | Model Risk Management requirements | R. Chen | Council |  | Active | AI-OS/Topics/mrm.docx | 1 | 0 | 0
genai-policy | GenAI usage policy | T. Nguyen | Council |  | Active | AI-OS/Topics/genai-policy.docx | 0 | 1 | 1
vendor-copilot | Vendor agent-assist pilot | S. Ruiz | Front door |  | Active | AI-OS/Topics/vendor-copilot.docx | 1 | 1 | 1
chat-deflection | Chat deflection FAQ assistant | Digital team | Standup | AIUC-108 | Active | AI-OS/Topics/chat-deflection.docx | 1 | 1 | 0
Note on A1: Short slug, lowercase, hyphens. Used everywhere else.
Note on D1: Front door, Standup or Council: where its decisions get made.
Note on E1: Label or key prefix that ties issues to it.
Note on F1: Active, Paused, Closed.
Note on G1: OneDrive path to its running notes.
Note on H1: Computed. Cowork never writes here.
Note on I1: Computed. Cowork never writes here.
Note on J1: Computed. Cowork never writes here.

## People
Name | Role | Team | Works with me on | How they work | Source | Last updated
M. Okafor | AI Council chair | Enterprise AI | council | Wants decisions framed as options with a recommendation. | Meeting | 2026-09-08
R. Chen | Model Risk lead | Model Risk Management | mrm, fraud-alerts | Prefers written questions by email; replies in 2 days. | Email | 2026-09-11
D. Patel | Contact center product owner | Customer Care | call-summary | Teams first; likes a weekly number. | Teams | 2026-09-13
T. Nguyen | Compliance partner, GenAI | Compliance | genai-policy | Needs the policy clause cited, not paraphrased. | Email | 2026-09-22
K. Ito | Fraud analytics lead | Fraud Operations | fraud-alerts |  | Meeting | 2026-09-23
L. Brooks | Complaints operations manager | Customer Care | complaint-triage |  | Meeting | 2026-09-21
Note on D1: Topics, comma-separated. Support Guide routes by this.
Note on E1: Facts only: prefers Teams, wants a one-pager before Council. Nothing evaluative; that goes in Private.

## Commands
Say this in Cowork | What happens | Group
start my day | Refresh Jira if the snapshot is stale, read the Dashboard, sweep yesterday's email, Teams and calendar, and give me the Needs You list plus anything worth logging. | Daily
refresh dashboard | Pull Jira through the connector (or the newest CSV export), rewrite the Jira sheet, stamp the snapshot. | Daily
log this: <note> | Capture a note into the Inventory as New, Know or Decision, with source, channel and confidence. | Inventory
add note to <topic>: <note> | Same as log this, filed against a named topic. | Inventory
confirm <INV-id> | Append a Confirmed row for a second-hand item. | Inventory
decide <INV-id>: <outcome> | Close an open decision or conflict by appending a Resolved row. | Inventory
what's open on <topic> | Open decisions, unconfirmed items, conflicts and Jira issues for one topic. | Inventory
done: <accomplishment> | Append to the Done log under today. | Reporting
draft weekly report | Build this week's report from the logs, email, Teams and calendar. Word draft, never sent. | Reporting
prep for <meeting> | Agenda from open items and Jira issues for the topics that forum owns. Word draft. | Reporting
review this | Run the Review Gate. Report what passes, what fails and the fix. Never rewrite. | Quality
support: <question> | Answer from the Answers log or a traceable source, or route to a named person. Log it. | Quality
draft Jira update for <KEY> | Write a status comment for that issue as a draft. Never posted. | Jira
what's stale in Jira | Issues past their stage's staleness limit, worst first, with owner. | Jira
move <file> to <folder> | Move it, fix every reference, log it on Changes. | Upkeep
check integrity | Scan the workbook for broken refs, duplicate IDs, unmapped statuses, and anything that looks like customer data. | Upkeep

## Config
Config
Blue cells are yours to set once. Grey cells are written by Cowork or computed. Nothing here is a secret: no tokens or passwords, ever.
Settings
Your name (as Jira shows it) | Sample PM | Used to pick out issues assigned to you.
Jira site URL | https://example.atlassian.net | No trailing slash. Builds the issue links.
Jira project key(s) | AIUC | Comma-separated, e.g. AIUC, GENAI
Jira scope in plain words | All issues in AIUC that are not Done, plus anything closed in the last 30 days | What Cowork asks the connector for. Plain English, not JQL: the Copilot connector is search, not a query engine.
Sample data as-of date | 2026-10-02 | Leave BLANK for real use. When set, every age is measured from this date so sample data stays coherent.
Today (computed) | 2026-10-02 | Do not edit.
Thresholds
Open decision: warning after (days) | 3
Open decision: critical after (days) | 7
Unconfirmed item: warning after (days) | 5
Jira snapshot: stale after (days) | 1
Snapshot age (days) | 0
Jira snapshot (written by Cowork on every refresh)
Snapshot pulled at | 2026-10-02 08:41 | Written by Cowork on every Jira refresh.
Snapshot source | Copilot connector (Jira Cloud) | Copilot connector, or CSV export + file name.
Issues in snapshot | 16 | Written by Cowork. Compared to the last refresh to catch a short pull.
Stages (the operating model's eight) |  |  | Jira status → stage map
Stage | Stale after (days) | Gate owner | Jira status (exact) | Stage
Intake | 7 | Portfolio Lead | Backlog | Intake
Triage | 7 | PM Owner | To Do | Intake
Discovery | 10 | PM Owner | Open | Intake
Design | 14 | Model Risk & Monitoring | Intake | Intake
Approval | 14 | AI Council | Triage | Triage
Delivery | 14 | Delivery Lead | Discovery | Discovery
Scale | 14 | Product Owner | Design | Design
Value | 45 | Finance Partner | In Review | Approval
|  |  | Governance Review | Approval
|  |  | Approval | Approval
|  |  | In Progress | Delivery
|  |  | In Delivery | Delivery
|  |  | Build | Delivery
|  |  | Scaling | Scale
|  |  | Rollout | Scale
|  |  | Value Tracking | Value
|  |  | Measuring | Value
|  |  | Done | Closed
|  |  | Closed | Closed
|  |  | Declined | Closed
|  |  | Transferred | Closed
|  |  | Won't Do | Closed
Add your workflow's statuses in the blank rows. Stage must be one of the eight, or Closed.

## Read Me
AI Operating System
SAMPLE | This copy holds illustrative data dated around 2026-10-02. Every age is measured from that date (Config › Sample data as-of). Use AI-OS.xlsx for real work.
What this is | The system of record for your desk. Cowork appends rows to the log sheets; the Dashboard recomputes from them against today's date. Nothing on the Dashboard is typed by hand.
Which cells | Blue headers are inputs. Grey headers and grey cells are formulas: never type over them. Add a row by filling the first empty row's blue columns. Never insert, delete or edit rows on a log sheet: append a correction instead.
Append-only | Inventory, Done, Answers, Reviews and Changes are logs. A decision is closed by a new Resolved row pointing at it (Ref), a rumour by a Confirmed row. The old row stays. OneDrive version history covers the Jira sheet, the only sheet that is replaced wholesale.
Privacy | Nothing from 1:1s, performance or career conversations goes in this workbook. That lives in AI-OS/Private. No customer data anywhere: case or ticket IDs only.
Sheets
Dashboard | Needs You, Jira attention, pipeline by stage, this week's accomplishments.
Inventory | Example row: INV-0019 ¦ 2026-10-05 ¦ Decision ¦ fraud-alerts ¦ Approve a second data engineer or slip Design a month ¦ K. Ito ¦ Meeting ¦ Confirmed ¦ ¦ AIUC-103
Jira | Snapshot of the issues in scope. Rewritten by 'refresh dashboard'. Example: AIUC-103 ¦ Fraud alert prioritization ¦ Design ¦ Epic ¦ Highest ¦ K. Ito ¦ 2026-06-29 ¦ 2026-09-14 ¦ 2026-09-28 ¦ Y ¦ fraud ¦ fraud-alerts
Done | Example row: 2026-10-05 ¦ Got MRM sign-off on the call summarization validation plan ¦ call-summary ¦ AIUC-101 ¦ Email
Answers | Support Guide log. Example: Q-0009 ¦ 2026-10-05 ¦ Who signs off a vendor model? ¦ Routed ¦ Routed to Third-Party Risk ¦ Third-Party Risk team ¦ A. Silva ¦
Reviews | One row per Review Gate run.
Changes | One row per file move or rename, with the references fixed.
Topics | One row per workstream. The slug in column A is the key every other sheet uses.
People | Facts about how people work. Nothing evaluative.
Commands | The phrases Cowork recognises.
Config | Jira site and project, staleness limits, the status → stage map, the snapshot stamp.